## Slide 1: Website for Vendor PPH Deduction Proof
PROJECT CHARTER – OCTOBER 2023

## Slide 2: Table of Contents
Project Background and Current Situation
2. Project Objective and Key Result
3. Project Scope
4. Business Process Flow
5. Project Deliverables
6. Project Schedule
7. Project Organization

## Slide 3: Project Background
Setiap bulan, Departmen Tax mengirimkan bukti potong PPh ke vendor secara manual melalui email.
Jumlah vendor dan bukti potong nya cukup banyak, sehingga proses ini membutuhkan banyak waktu.
Sering kali, vendor menanyakan kembali perihal bukti potong PPh yang telah dikirimkan oleh Department Tax.
Hal ini membuat Department Tax harus bekerja dua kali karena perlu melakukan pencarian dan pengiriman ulang terhadap file bukti potong PPh yang diminta vendor.
Project Background | 
Department Tax melakukan pelaporan PPh ke website DJP Online dan mengunduh bukti potong PPh dalam bentuk PDF, kemudian mengirimkan bukti potong secara manual by email sesuai dengan permintaan vendor.
Current Situation | 

## Slide 4: Table of Contents
Project Background and Current Situation
2. Project Objective and Key Result
3. Project Scope
4. Business Process Flow
5. Project Deliverables
6. Project Schedule
7. Project Organization

## Slide 5: Project Objective
Objective | 
Membuat website bukti potong PPh vendor untuk company TRIAS, TTA, TTE, dan UNS.
Key Result | 
Department Tax dapat mengunggah dokumen bukti potong PPh ke website.
Vendor dapat mengunduh secara mandiri dokumen bukti potong PPh yang diunggah ke website.
Department Tax tidak perlu mengirimkan dokumen bukti potong PPh secara manual melalui email kepada vendor.

## Slide 6: Table of Contents
Project Background and Current Situation
2. Project Objective and Key Result
3. Project Scope
4. Business Process Flow
5. Project Deliverables
6. Project Schedule
7. Project Organization

## Slide 7: Project Scope
Company
PT Trias Sentosa, Tbk.
PT Trias Toyobo Astria
File Type and Size
PDF File Type
File Size (per document) less than 500Kb
Expired Date
One year from first time uploaded
PT Toyobo Trias Ecosyar
PT Unggul Niaga Sentosa

## Slide 8: Table of Contents
Project Background and Current Situation
2. Project Objective and Key Result
3. Project Scope
4. Business Process Flow
5. Project Deliverables
6. Project Schedule
7. Project Organization

## Slide 9: Business Process Flow
Flow to Next Step
By Pass
Business Process in Website for Vendor PPH Deduction Proof
Business Process in Other System (email, phone, etc.)
Legend:
Background Process
Scenario : Share Link Folder
Notes: Tambah mockup kasaran dulu

## Slide 10: Business Process Flow
Flow to Next Step
By Pass
Business Process in Website for Vendor PPH Deduction Proof
Business Process in Other System (email, phone, etc.)
Legend:
Background Process
Scenario : Reset Folder Password
Notes: Kolom vendor di kiri

## Slide 11: Mock Up
Login Page
Notes: Kolom vendor di kiri

## Slide 12: Mock Up
Dashboard
Notes: Kolom vendor di kiri

## Slide 13: Mock Up
Share Link
1
2
Notes: Kolom vendor di kiri

## Slide 14: Mock Up
Vendor Company

## Slide 15: Mock Up
Vendor Page
Notes: Setelah multi clean, harus nya folder per company dulu, baru di dalam nya ada pdf multi clean

## Slide 16: Mock Up
Update Folder Password
1
2
3
4
Notes: Kolom vendor di kiri

## Slide 17: File Distribution Process
File name
8296749936030002022110.zip
Digit 1-15 | 829674993603000 | NPWP TTE
Digit 16-21 | 202211 | Year – Month
upload
Vendor A
Vendor B
Vendor C
File name
Download zip file from DJP Online Website
Vendor A
Vendor B
Vendor C
9096749936030002022110.zip
Digit 1-15 | 909674993603000 | NPWP TS
Digit 16-21 | 202211 | Year – Month
upload
Download zip file from DJP Online Website
Website Bukti Potong PPh Vendor
Vendor A
Vendor B
Vendor C
Un-ZIP and Create Folder
Create Folder
TTE
File PPh 1
File PPh 2
File PPh 3
TS
File PPh 1
File PPh 2
File PPh 3
TTE
File PPh 1
File PPh 2
File PPh 3
TS
File PPh 1
File PPh 2
File PPh 3
TTE
File PPh 1
File PPh 2
File PPh 3
TS
File PPh 1
File PPh 2
File PPh 3
Move file
Shareable link
Shareable link
Shareable link

## Slide 18: File Distribution Process
File name
8296749936030002022110.zip
Digit 1-15 | 829674993603000 | NPWP TTE
Digit 16-21 | 202211 | Year – Month
upload
Vendor A
Vendor B
Vendor C
File name
Vendor A
Vendor B
Vendor C
9096749936030002022110.zip
Digit 1-15 | 909674993603000 | NPWP TS
Digit 16-21 | 202211 | Year – Month
Download zip file from DJP Online Website
Vendor A
Vendor B
Vendor C
Un-ZIP and Create Folder
Create Folder
TTE
File PPh 1
File PPh 2
File PPh 3
TS
File PPh 1
File PPh 2
File PPh 3
TTE
File PPh 1
File PPh 2
File PPh 3
TS
File PPh 1
File PPh 2
File PPh 3
TTE
File PPh 1
File PPh 2
File PPh 3
TS
File PPh 1
File PPh 2
File PPh 3
Move file
Shareable link
Shareable link
Shareable link
Website for Vendor PPH Deduction Proof
download

## Slide 19: Table of Contents
Project Background and Current Situation
2. Project Objective and Key Result
3. Project Scope
4. Business Process Flow
5. Project Deliverables
6. Project Schedule
7. Project Organization

## Slide 20: Project Deliverables
Phase | Activities | Deliverables | Status
PREPARE | Project Initiation | Project Scope & Schedule are Defined | In Progress
 | Discovery and Evaluation | Solutions are Discovered and Evaluated | In Progress
EXPLORE | Business Blueprint Design | Business Blueprint Design is Documented | Planned
 | Business Blueprint Confirmation | Business Blueprint Design is Approved | Planned
 | Enhancement (RICEF) Design | RICEF Design is Documented | Planned
 | Authorization Requirement and Design | Authorization Requirements and Design is Completed and Documented | Planned
REALIZE | Enhancement (RICEF) Development | RICEF Design is Developed | Planned
 | Run Scenario Test and Integration Test | Scenario and Integration Test are executed and Issues are resolved | Planned
 | Prepare UAT and EUT Delivery | User Acceptance Test Material and Documentation are ready | Planned
 |  | End-User Training Material and Documentation are ready | Planned
DEPLOY | User Acceptance Test (UAT) | User Acceptance Test is approved | Planned
 | End-User Training (EUT) | End-Users are trained | Planned
 | Prepare Production Environment | Production System Environment is ready | Planned
RUN | Go Live | Live Production Environment | Planned
 | Support After Go Live | Functional or Technical Issues are Solved | Planned

## Slide 21: Table of Contents
Project Background and Current Situation
2. Project Objective and Key Result
3. Project Scope
4. Business Process Flow
5. Project Deliverables
6. Project Schedule
7. Project Organization

## Slide 22: Project Schedule
Legend:
Planned
In Progress
Done
Proposed Milestone
Finished Milestone
Notes: Kick-off - Dec

## Slide 23: Table of Contents
Project Background and Current Situation
2. Project Objective and Key Result
3. Blueprint Confirmation
4. Business Process Flow
5. Project Deliverables
6. Project Schedule
7. Project Organization

## Slide 24: Project Organization
Steering Committee
Putu Bagiarsa, Hennie Susanto, Adi Yuda
Business Process Owner
Hennie Susanto
Solution Architects
Adi Yuda, Yunita
Process Expert
Consultant
Frontend Developer
Backend Developer
Bunga Rizki A, Samuel Gustaf
Filla Sartika
Dary Saputra A, Oskar Andreas
M Royyan Z
Project Manager
Ryan Haris R
Notes: Kick-off - Dec

## Slide 25: Thank You